## Plan
ID | Task Name |  | Task Owner | Start Date | End Date | Status | Duration | 2021-04-01 |  |  |  | 2021-05-01
[8 empty] | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
1 | INITIATION & PLANNING
| 1.1 | Defining/Scoping of the project | Vishal R | 2021-04-15 | 2021-04-15 | Completed | 1 day | bar: 2021-04-01 W2
| 1.2 | Dependencies | Raghavendra | 2021-04-19 | 2021-04-22 | In-Progress | 4 days
| a. | FTP server details | Raghavendra | 2021-04-21 | 2021-04-22 | In-Progress | 2 days
| b. | White listing of login credentials | Raghavendra | 2021-04-21 | 2021-04-22 | In-Progress | 2 days
| c. | File Path | Raghavendra | 2021-04-20 | 2021-04-21 | Completed | 2 days
| d. | Sample .csv file | Raghavendra | 2021-04-20 | 2021-04-21 | Completed | 2 days
| e. | Gateway ID's | Raghavendra | 2021-04-20 | 2021-04-21 | Completed | 2 days
2 | EXECUTION
| 2.1 | Deliverables | Paramananda | 2021-04-21 | 2021-04-30 | In-Progress | 8 days | bar: 2021-04-01 W3 to 2021-04-01 W4
| a. | Establishing connection with FTP server | Paramananda | 2021-04-21 | 2021-04-23 | In-Progress | 3 days
| b. | Read .csv file data from FTP server | Paramananda | 2021-04-26 | 2021-04-27 | Not started | 2 days | bar: 2021-04-01 W4
| c. | Parse .csv file data into Zonos format in run-time | Paramananda | 2021-04-28 | 2021-04-29 | Not started | 2 days | bar: 2021-04-01 W4
| d. | Pushing data to Zonos Platform based on OBIS code | Paramananda | 2021-04-30 | 2021-04-30 | Not started | 1 day | bar: 2021-04-01 W4
3 | CLOSURE
| 3.1 | Monitoring/Visualization of Data on the platform | Vishal R | 2021-05-03 | 2021-05-05 | Not started | 3 days | bar: 2021-05-01 W1